## board status - checkouts
| Board | Memory | Rework performed | Visual inspection | 3v3/GND net | Batt/GND net | 3V3 | Bootloader | Crystal | USB Data | USB powering SAMD | USB charging | UART | SPI | I2C | SD | CircuitPython | CircuitPython version | Radio setup | Near field TX | Near field RX | Cleaning | LTC4121 | Burn Wires | REPL power draw (idle) | REPL (low power) | Deep Sleep | Shallow Sleep
1 | Yonkers | mram | replaced J19 chip with fresh J20 after initial bootup | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE (inferred) | TRUE | TRUE | TRUE | N/A (no GPS) | inferred from radio | inferred from power monitor | TRUE | TRUE | 8.0.3 | TRUE | TRUE | TRUE | TRUE | TRUE | Untested | 123.84 mW | 115.92 mW | 26.64 mW | 55 mW
2 | Schenectady | mram | repaired USB-C connector | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | intermittent | FALSE (disabled) |  | N/A (no GPS) | inferred from radio | inferred from power monitor | TRUE | TRUE | 8.0.3 | TRUE | TRUE | TRUE | TRUE | TRUE | Untested

## issues
Board | Issue | Suspected root cause | Fix
Schenactady | Mounts intermittently as a USB device, charging flaky | Pad ripped off USB-C connector | switch to micro-USB